## Partner: FTZ – Fondazzjoni Temi Zammit	 	Date:   31/03-2010

Period covered by this Review: 1 Jan. 2010 to 31 Mar. 2010

Please complete this form to record the activities and progress in the period.

| Communication: Which partners have you had communications with? How often and in which way have you communicated with partners? | We have been in contact with all partners. Most communication has been by e-mail and Facebook. E-mail have been sent to / received from all partners almost on a weekly basis. |
| --- | --- |
| Innovatory aspects: Describe any innovatory aspects to your activities. | The project has plenty of innovatory aspects in itself. The challenge is that will be many language teachers will create their own materials suitable for computer assisted language teaching in additional to traditional teaching materials, books and manuals. |
| Management: Do you feel that information relating to the management of the project is sufficient, relevant and effective? (Please comment). Give a rating on a scale of 5 to 1. 5 being the most positive. | We feel that management has been working well. However, It has been a problem that the Spanish National Agency mailed very late the signed contract to CECE and that we therefore didn’t receive the first part of the grant in order to start to work in due time on the project. 4 |
| Dissemination: List of dissemination activities you have been engaged in. | We translated the brochure into Maltese and sent it in January to a database of 250 users. We have made use of Facebook to communicate about the project. We have made use of other EU partnerships and projects to disseminate about Pools-2. |
| External impact/mainstreams: Any multiplier effect/impact. |  |
| Overall comment: |  |

Summary of Local Activities in the period: We translated the first brochure in Maltese. We have made use of Facebook to communicate about the project. We have made use of other EU partnerships and projects to disseminate about Pools-2. We started to verify and update the CALL course book. The book will also updated with a unit on social spaces, such as Facebook and Linkedln. It will be sent to all partners for peer review. It will translated by September before the next workshop will be held in Malta.

Milestones met: Translated the first brochure in Maltese. Started to disseminate the project.

Delays (if any) in planned activities and outputs: The problems due to the late contracting and financing and some internal problems have impeded to start the project activities as scheduled on the application.

If applicable how will the team compensate for the delays and catch up:

Other comments: